# Business case: Automating monthly PMO reporting across a 40-project portfolio

Structured on the HM Treasury Five Case Model. Recommended option: Buy a SaaS PPM tool.  Prepared by Divyaprakash S M.

# Executive summary

Recommendation: approve Buy a SaaS PPM tool. Over 5 years it delivers a net present value of £239k and a benefit-cost ratio of 1.66 (medium value for money), paying back in 1.9 years.

Risk: across 10,000 simulated outcomes it pays for itself 96% of the time and is the best option in 97% of them. The middle outcome (P50) is £160k; a bad outcome (P10) is £41k.

Key sensitivity: the answer depends most on annual benefit. Benefits could fall 40% before the option stops paying for itself.

# 1. Strategic case

## Case for change

Monthly status reporting across the 40-project portfolio is compiled by hand from six different trackers. It absorbs roughly 80 analyst-days a month, reports are a week old by the time the board reads them, and figures regularly disagree between packs. Leadership wants decisions made on current, single-source data.

## Objectives

Cut reporting effort by at least 60%; deliver reports within 2 working days of month end; one source of truth for cost, schedule, risk and resourcing data.

# 2. Economic case

Options are appraised over 5 years at a 3.5% discount rate. Costs carry a 15% optimism-bias uplift (plus option-specific delivery-risk uplifts) and benefits a 10% haircut, in line with Green Book guidance that early estimates are systematically optimistic.

| Option | PV costs | PV benefits | NPV | BCR | Value for money | Payback |
| --- | --- | --- | --- | --- | --- | --- |
| Do minimum (keep manual) | £0k | £0k | £0k | baseline | - | - |
| Buy a SaaS PPM tool | £360k | £599k | £239k | 1.66 | Medium | 1.9 years |
| Build in-house dashboard | £312k | £508k | £196k | 1.63 | Medium | 2.5 years |

## Risk analysis

| Option | P10 NPV | P50 NPV | P90 NPV | Chance NPV > 0 | Chance best option |
| --- | --- | --- | --- | --- | --- |
| Buy a SaaS PPM tool | £41k | £160k | £240k | 96% | 97% |
| Build in-house dashboard | £29k | £130k | £195k | 95% | 3% |

Simulation ranges: costs -10% to +30%, benefits -30% to +10%, 20% chance benefits start a year late.

## Sensitivity and scenarios

| Driver (±20%) | NPV if lower | NPV if higher | Swing |
| --- | --- | --- | --- |
| Annual benefit | £119k | £359k | £239k |
| Annual running cost | £291k | £187k | £104k |
| Year-1 implementation cost | £253k | £225k | £28k |
| Discount rate | £246k | £232k | £14k |
| Upfront cost | £245k | £233k | £12k |

| Scenario | NPV | BCR | Payback |
| --- | --- | --- | --- |
| Pessimistic | £46k | 1.11 | 3.7 years |
| Base | £239k | 1.66 | 1.9 years |
| Optimistic | £336k | 2.02 | 1.6 years |

# 3. Commercial case

Procure via an existing public-sector framework (e.g. G-Cloud) to shorten the timeline. Three-year term with a two-year extension option; data export rights and exit support written into the contract.

# 4. Financial case

Cash required by year for the recommended option (including optimism bias):

| Year | Costs | Benefits | Net | Cumulative |
| --- | --- | --- | --- | --- |
| 0 | £30k | £0k | -£30k | -£30k |
| 1 | £130k | £74k | -£55k | -£85k |
| 2 | £58k | £148k | £91k | £6k |
| 3 | £58k | £148k | £91k | £96k |
| 4 | £58k | £148k | £91k | £187k |
| 5 | £58k | £148k | £91k | £278k |

Peak funding requirement is £85k (the lowest point of cumulative cash flow), which is the budget that must be secured up front.

# 5. Management case

Senior Responsible Owner: Programme Director. Delivery via a 6-month phased rollout with a pilot on 5 projects. Benefits owned by named individuals and reviewed quarterly at the portfolio board; the business case is re-validated at each stage gate.

Benefits will be tracked quarterly against this case. If the re-forecast NPV turns negative, the project will be returned to the board for a stop / continue decision (continued business justification).